## Sheet1
Project Name | JFK Shopping cart and Donation System
Project Manager | Lois Anne G. Logronio
Requirement ID | Requirement Description | Requirement Type | Status | Priority | Software Module | Test Case Number | Tested In
R1 | Easy to use interface | Highly Needed | In Progress | High | User Interface
R2 | Has a login for admin | Highly Needed | Completed | High | Back End Login
R3 | Admin can login | Highly Needed | In Progress | High | Back End Login
R4 | Admin has control on volunteer and subscribe module | Highly Needed | In Progress | High | Back End module
R5 | User can donate online | Highly Needed | In Progress | High | Donation Module
R6 | User can shop online | Highly Needed | In Progress | High | Shopping Cart Module
R7 | Any user can view the foundation's programs | Lowy Needed | Completed | Low | User Interface | UITC_Ev1
R8 | User can cancel his/her donation | Highly Needed | In Progress | High | Donation Page
R9 | User can stop subscribing | Lowly Needed | In Progress | Low | Volunteer Page
R10 | Admin can view records of volunteers | Highly Needed | In Progress | High | Back End Volunteer Module
R11 | Admin can view records of subscribers | Highly Needed | In Progress | High | Back End Subscriber Module | UITC_SeEm1
R12 | Admin can approve requests | Highly Needed | In Progress | High | Back End Volunteer Module | UITC_ApAp1
R13 | Admin can reject requests | Highly Needed | In Progress | High | Back End Volunteer Module | UITC_ReAp1
R14 | User can select many items in the shop | Highly Needed | In Progress | High | Shopping Cart Module
R15 | Payment transaction is secured | Highly Needed | In Progress | High | Donation and Shopping Cart Module