## Sheet1
Number | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R1 | 4 | Defective Computer | One of the computer in the work station doesn't work |  | Inputed Virus | Antivirus is not effective | Change AntiVirus |  | Low | Low | I.T. Department will repair the computer by removing the virus and changing the AntiVirus
R2 | 5 | Unfamiliar environment | The person incharge to handle the system might not be familiar with the framework that has been used to create the system |  | Framework used to develop the system | Unfamiliarity of the framework used | Training |  | Low | High | Employees will be trained / Hiring someone who is knowledgable in that field
R3 | 3 | Not meeting the deadline for documentation | Modifications in the documentation, Delayed submission of documents |  | Revisions on the documentation | Changes Made | Division of Work |  | Low | High | Project Leader and Team Members will divide the work
R3 | 2 | System Errors | System doesn't fully run |  | Coding Error |  | Check all the codes for errors |  | High | High | Debugging
R4 | 1 | Insufficient Information | Client Meeting must be conducted |  | Client Meeting is not regularly held |  | Schedule Meeting |  | Low | High

## Sheet2
PRE
Number | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R1 | 1 | Data Lost | Data could be lost if the server crashes
R2 | 2 | Insufficient Information | Client Meeting must be conducted
R3 | 4 | Unfamiliar environment | The person incharge to handle the system might not be familiar with the framework that has been used to create the system
R4 |  | Social Engineering |  |  |  | anymore |  |  |  |  | computer by removing the virus
R5 | [10 empty] | and changing the AntiVirus
R6 | 3 | Over Budget | Excess money came back after the 1st milestone | People Risk | Budget for the project | Cost estimate not | Lower the budget | Project Manager | Medium | Medium | Revise cost estimate
R7 |  |  |  |  | overlooked by the PM | planned well
R8 | 2 | Not meeting the | Database and Airline Module is still under | Time Risk | Developers are having | Understaff | Hire programmer | HR Dept. | Medium | High | Hire additional programmer/s