## Sheet1
Number | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R1 | 3 | Hosting ended | Hosting of APC ends after the finals | Technical Risk | none | Project may not be able | P1: buy the hosting server | Finance Dept. & I.T. Dept. | Medium | High | Will use the company owner's another
[6 empty] | to continue | P2: look for free hosting server |  |  |  | system's hosting server
R2 | 2 | Documents not finished | Creating documents not finished on time for static testing | Time Risk | Many revisions and | May fail the static testing | P1: submit only what the team has | I.T. Dept. | High | High | I.T. Department will extend time to
|  | on time |  |  | wrong time management |  | finished |  |  |  | finish doing the documents for static
[7 empty] | P2: extend time on doing the documents |  |  |  | testing
to meet the submission time
R3 | 4 | No Maintenance | No maintenance for the system after deployment | People Risk | Didn't include on project's | Owner may not be updated | include it already on the project's plan | HR Dept. | Medium | Medium | Revise cost project planning and
[5 empty] | planning phase | on what's going on with the |  |  |  |  | analysis documents
with the system
R4 | 1 | Not finishing the | Donation and Shopping Cart Modules are still under | Time Risk | RC1: Developers are trying | Deployment of the system | P1: abort using extension and find | I.T. Dept. | High | High | Just redirect the site to paypal's
|  | system before the | development |  | to use paypal extension | may be extended | another way. |  |  |  | payment form and extend working
|  | finals |  |  | for the online transaction |  | P2: Hire programmer |  |  |  | hours
RC2: One of the
prgrammers could not
because of health issues
R5 | 5 | Client meeting not | Meeting with the client not performed | Technical Risk | Client cancels the meeting | Updates and progress not | Client meeting rescheduled | I.T.Dept | Low | Low | Set another date and time for the
|  | conducted |  |  |  | informed to the client |  |  |  |  | meeting

## Sheet2
PRE
Number | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R1 | 1 | Data Lost | Data could be lost if the server crashes
R2 | 2 | Insufficient Information | Client Meeting must be conducted
R3 | 4 | Unfamiliar environment | The person incharge to handle the system might not be familiar with the framework that has been used to create the system
R4 |  | Social Engineering |  |  |  | anymore |  |  |  |  | computer by removing the virus
R5 | [10 empty] | and changing the AntiVirus
R6 | 3 | Over Budget | Excess money came back after the 1st milestone | People Risk | Budget for the project | Cost estimate not | Lower the budget | Project Manager | Medium | Medium | Revise cost estimate
R7 |  |  |  |  | overlooked by the PM | planned well
R8 | 2 | Not meeting the | Database and Airline Module is still under | Time Risk | Developers are having | Understaff | Hire programmer | HR Dept. | Medium | High | Hire additional programmer/s